## Slide 1: Project Management & Research Methodology (IS4S706)
Approaches to
Project Management

## Slide 2: Outline
Project management approaches
  Waterfall
  Incremental
  Iterative
  AGILE
  Scrum
  Prince 2
  PMI
  ….
  ….

## Slide 3: Waterfall model
One-shot or once-through approach
Each stage cascades into the next
Stages occur in strict sequence
Stage only starts when previous stage is complete
Planning and quality control are key
Works well when requirements are clearly defined
Works well when there is little change
Traditionally used widely for IT projects

## Slide 4
Requirements
Design
Implement
Test
Deploy
Maintain
The Waterfall model

## Slide 5
A (modified) Waterfall model
This version of the Waterfall model described in Bob Hughes’ book offers possible improvement of the original in that it provides some scope for re-working stages once they have been completed.
The approach provides for feedback loops that are activated when there is a need to revisit an earlier stage (e.g. to re-design or recode)
This could well require extensive re-planning
There are quality control activities at each phase in an attempt to limit the need to revisit phases after they are signed off
Requirements
Design
Implement
Test
Deploy
Maintain

## Slide 6: Waterfall model advantages
Encourages good requirements elicitation and system design up-front. This can lead to a more efficient project as a whole
  For example, a bug or problem found during elicitation or design stages is cheaper to fix (in terms of money, time and effort) than the same (or consequential) problem found later in the process
Places great emphasis on documentation
  Useful should a team member leave (without good documentation much knowledge would otherwise be lost)
It is a simple, highly structured approach
  Some people simply prefer this

## Slide 7: Waterfall model disadvantages
Many believe it is not practical (and likely impossible) to get one phase of a non-trivial software project lifecycle perfected before moving on to the next
  Client might change requirements – maybe they were not fully aware of what was possible at the early stage of the lifecycle. If waterfall approach strictly applied, then project needs to start again.
  A great design might turn out to be impossible (or not cost-effective) to implement

## Slide 8: Incremental model
Similar in some ways to waterfall model
However, it involves development and delivery of functionality in fragments or increments
Global requirements and global design are produced first
Then
  Product is produced in increments
  Each increment consists of low-level requirements elicitation and analysis, low-level design, construction, testing and installation
  Users get their new system in instalments
  Early increments might not have the less important features of the system, these having been dropped in order that deadlines are met. The dropped features can be implemented in subsequent increments
Well suited to larger projects, and where requirements are relatively well known

## Slide 9
An Incremental model
Often used in conjunction with timeboxes:
Deadline for completion of an increment is fixed.
Features to be delivered by each increment are ranked according to importance.
Least important features may be dropped to ensure deadline is met.
Dropped features can be implemented in a subsequent increment if still required.
Global requirements
Global design
Increment 1
Low-level requirements
Low-level design
Implement
Test
Increment 2
Low-level requirements
Low-level design
Implement
Test
Increment 3
Low-level requirements
Low-level design
Implement
Test
Delivered system
(based on diagram taken from Project Management for IT-Related Projects, Bob Hughes, BCS)
Deploy
Deploy
Deploy

## Slide 10: Iterative model
Suited to projects where
  Requirements are not clearly understood
  There is a need to begin development quickly in order to produce a version of the product that will demonstrate its look and feel
Allows customer to identify and refine requirements and design features
A risk with this approach is not knowing when to stop iterating; the approach is difficult to monitor and control
Key terms
  Collaboration
  Continuous Improvement

## Slide 11
Iteration 1, 2, 3…
Requirements review
Low-level design
Implement
User testing
Initial requirements analysis
Initial design
Application version 1
Application version 2
Application version 3
Operational system
Final version ?
Yes
No
An Iterative model
(based on diagram taken from Project Management for IT-Related Projects, Bob Hughes, BCS)

## Slide 12: Agile project management
What is Agile?
  Collaborative
  Iterative
  Continuous testing and delivery
  Responsive
No single Agile methodology
A response to shortcomings of “heavyweight” methodologies (e.g. Waterfall)
Agile manifesto (2001)
https://www.agilealliance.org/

## Slide 13: Agile Manifesto
We are uncovering better ways of developing software by doing it and helping others do it. Through this work we have come to value:
Individuals and interactions over processes and tools
Working software over comprehensive documentation
Customer collaboration over contract negotiation
Responding to change over following a plan
That is, while there is value in the items on the right, we value the items on the left more.
© 2001-2020 Agile Manifesto Authors This declaration may be freely copied in any form, but only in its entirety through this notice

## Slide 14: Agile 12 Principles
1. Our highest priority is to satisfy the customer through early and continuous delivery of valuable software.
2. Welcome changing requirements, even late in development. Agile processes harness change for the customer's competitive advantage.
3. Deliver working software frequently, from a couple of weeks to a couple of months, with a preference to the shorter timescale
4. Business people and developers must work together daily throughout the project.
5. Build projects around motivated individuals. Give them the environment and support they need, and trust them to get the job done.
6. The most efficient and effective method of conveying information to and within a development team is face-to-face conversation

## Slide 15: Agile 12 Principles
7. Working software is the primary measure of progress.
8. Agile processes promote sustainable development. The sponsors, developers, and users should be able to maintain a constant pace indefinitely.
9. Continuous attention to technical excellence and good design enhances agility.
10. Simplicity - the art of maximizing the amount of work not done - is essential.
11. The best architectures, requirements, and designs emerge from self-organizing teams.
12. At regular intervals, the team reflects on how to become more effective, then tunes and adjusts its behaviour accordingly

## Slide 16: Agile frameworks
Scrum
AgilePM
Extreme Programming (XP)
Crystal
Kanban
Lean Software Development
Scrum of Scrums
….
….

## Slide 17: Scrum
Scrum is an Agile framework for developing, delivering, and sustaining complex products.
Ken Schwaber and Jeff Sutherland (n.d.), “The Scrum guide”, available at www.scrum.org
Scrum is:
  Lightweight
  Simple to understand
  Difficult to master
Scrum is not a process, technique, or definitive method. Rather, it is a framework within which you can employ various processes and techniques.
The Scrum framework consists of Scrum Teams and their associated roles, events, artifacts, and rules. Each component within the framework serves a specific purpose and is essential to Scrum’s success and usage.
The rules of Scrum bind together the roles, events, and artifacts, governing the relationships and interaction between them.

## Slide 18: Scrum terminology
Sprint
Roles
  Scrum Team
  Product Owner
  Scrum Master
Artifacts
  Product Backlog
    User Stories
  Sprint Backlog
  Burndown Chart
Ceremonies
  Sprint Planning
  Daily Scrum / Stand-up
  Sprint Review/ Retrospective
Definition of Done
Potentially shippable product

## Slide 19: Scrum video
https://www.youtube.com/watch?v=9TycLR0TqFA

## Slide 20: PRINCE2
PRINCE
  PRojects IN Controlled Environments
  1989
  First established by the Central Computer and Telecommunications Agency
  Divides projects into manageable and controllable stages
PRINCE2
  1996
  De Facto standard and used extensively by UK government
  Widely recognised and used in private sector, both in UK and internationally (generally Europe and Australia)
  AXELOS Ltd
  Certification
PRINCE2 Agile

## Slide 21: PRINCE2 – 4 integrated elements
Principles
  Continued business justification
  Learn from experience
  Defined roles and responsibilities
  Manage by stages
  Manage by exception
  Focus on products
  Tailor to suit the project environment

## Slide 22: PRINCE2 – 4 integrated elements
Themes
  Business case
  Organization
  Quality
  Plans
  Risk
  Change
  Progress

## Slide 23: PRINCE2 – 4 integrated elements
Processes
  Starting up a project
  Directing a project
  Initiating a project
  Controlling a stage
  Managing product delivery
  Managing stage boundaries
  Closing a project
Project Environment

## Slide 24: PRINCE2 video
PRINCE2 explained in 30 minutes - YouTube

## Slide 25: Project Management Body of Knowledge
PMBOK
Describes standard project management terminology, best practices and process guidelines
Project Management Institute
49 project management Processes
  overlap and interact throughout a project
  described in terms of inputs, tools, outputs
10 Knowledge Areas
  Integration, Scope, Time, Cost, Quality, Human Resource, Communications, Risk, Procurement, Stakeholder
5 Process Groups
  Initiating, Planning, Executing, Monitoring and Control, Closing

## Slide 26
Knowledge area | Project Management Process Groups |  |  |  | 
 | Initiating | Planning | Executing | Monitoring and Control | Closing
Project Integration Management | Develop project charter | Develop project management plan | Direct and manage project work Manage project knowledge | Monitor and control project work Perform integrated change control | Close project
Project Scope Management |  | Plan scope management Collect requirements Define scope Create WBS |  | Validate scope Control scope | 
Project Schedule Management |  | Plan schedule management Define activities Sequence activities Estimate activity durations Develop schedule |  | Control schedule | 
Project Cost Management |  | Plan cost management Estimate costs Determine budget |  | Control costs | 
Project Quality Management |  | Plan quality management | Manage quality | Control quality | 
Project Resource Management |  | Plan resource management Estimate activity resources | Acquire resources Develop team Manage team | Control resources | 
Project Communication Management |  | Plan communications management | Manage communications | Monitor communications | 
Project Risk Management |  | Plan risk management Identify risks Perform qualitative risk analysis Perform quantitative risk analysis Plan risk responses | Implement risk responses | Monitor risks | 
Project Procurement Management |  | Plan procurement management | Conduct procurements | Control procurements | 
Project Stakeholder Management | Identify stakeholders | Plan stakeholder engagement | Manage stakeholder engagement | Monitor stake holder engagement | 

## Slide 27: What’s coming next…
Scope management
Schedule managment