## Slide 1: Project Management & Research Methodology (IS4S706)
Scope Management

## Slide 2: Project management body of knowledge
This lecture makes use of ideas and information taken from the Project Management Body of Knowledge
  Widely accepted standard in Project Management (particularly in the US)
  Overseen by the Project Management Institute
  Internationally recognized PMP certification

## Slide 3: Definitions
Product scope
  The features and functions of the product or service that you and your team are building
Project scope
  The work that needs to be done to make the product
Scope creep
  Uncontrolled changes that cause the project team to do extra work

## Slide 4: Scope Management processes
Plan Scope Management
Collect requirements
Define scope
Create Work Breakdown Structure (WBS)
Control Scope
Validate Scope

## Slide 5: Plan Scope Management
Plan out the work required for defining and controlling project scope
This will involve
  Expert judgment
  Data analysis
  Team meetings
Outputs
  Scope management plan

## Slide 6: Collect requirements
Finding out what the project stakeholders want
Needed for
  Project definition
  Project monitoring
  Project closure

## Slide 7: Collect requirements
Involves
  Elicitation
    Interviews
    Focus groups
    Facilitated workshops
    Questionnaires (for bigger groups)
    Demonstrating prototypes
    Observing
  Making decisions
    Unanimity
    Majority
    Plurality
    Dictatorship

## Slide 8: Collect requirements
Output will be
  A requirements document
    Functional (e.g. features)
    Non-functional (i.e. quality attributes)
  Requirements traceability matrix
    Where requirements came from
    Where they get implemented
    How they get verified

## Slide 9: Requirements document example
Holiday Cottages Web Site Requirements Document
1. Introduction
The web site enhancement will allow on-line booking…….
2. Organization impact
The product will have a positive impact on company profits, primarily through increased sales…….
3. Functional requirements
4. Non-Functional requirements
NAME | FR1 – Register customer
Summary | The new system must allow new customers to register
Rationale | Registration will encourage customers to return to site by speeding up transaction times of return visits
Requirement | Customers must be able to register personal and payment details. GDPR compliance is essential.
NAME | FR2– Allow site visitors (not registered)
Summary | The new system must allow visitors to make purchases
Rationale | Not all potential customers will want to register. Therefore the system must allow visitors to make guest purchases
Requirement | Unregistered visitors to site must be allowed to make purchases. Visitors must be able to browse, select and make one-off purchases of products. Payment will be via credit cart or PayPal, GDPR compliance is essential.
:
NAME | NFR1 – Throughput capacity
Summary | Peak-time transaction capacity of 10,000 per hour
Rationale | The new site is expected to attract between 1,000 and 3,000 visitors at peak-time (on average) – in order to maintain service and response times it is thought prudent to build extra capacity into the system from the start.
Requirement | The new system must be able to deal with up to 10,000 transactions (i.e. requests) per hour.
:

## Slide 10: Requirements traceability matrix example
Origin | Requirement | Module | Test Case | Status
Tom Baker | FR1 – Register customer | 3.3.1 | TC01-TC34 | Done
Jill Davies | FR2– Allow site visitors (not registered) | 3.4.1 | TC234-TC237 | In progress
Rob Jones | FR3-Secure purchase | 3.6.2, 3.7.1 | TC2 | On hold

## Slide 11: Define scope
Project scope
  All the work that the project team is going to do over the course of the project
Inputs are
  A requirements document
  Project charter
    A general description of project, outline schedule and business case and designated project manager
  Organizational process assets
    These provide information on how the organization normally runs its projects
    Guidelines and instructions for project management, procedures that need to be followed, templates for all the various documents that will be created
    Will include “Lessons learned”
Output
  Project scope statement
    This tells the project team what it has to do

## Slide 12: Define scope
Project scope statement
  Product scope description
  Project exclusions
  Project deliverables
  Project acceptance criteria
  Project constraints
  Project assumptions

## Slide 13: Define scope
Generating the project scope statement
  Product analysis
  Facilitated workshops (with project stakeholders)
  Expert judgment
  Think of alternative ways of doing the work

## Slide 14: Project scope statement example
Holiday Cottages Web Site Project Scope Statement
Project Scope Description. The project will enhance current web site by providing on-line booking functionality
Project Exclusions. The new functionality is not required to be integrated with other IT systems within the organisation.
Project deliverables.
Project acceptance criteria. A working web site enhancements to be deployed on or before agree date. All defects found must not have an adverse impact on existing systems. All defects found must be judged of low enough priority and severity to be acceptable to all stakeholders.
Project constraints. All new web pages must follow current house style. Backend (e.g. database) must use current IT infrastructure.
Project assumptions. Project team will work exclusively on this project throughout. Project team will adopt Waterfall methodology.
Online booking enhancement | Test plan | Source code | Schedule
Design documents | Test reports | Defect reports | Change management plan
Contract | Budget | Project management plan | Risk management plan

## Slide 15: Create Work Breakdown Structure (WBS)
Work Breakdown Structure (WBS)
  A hierarchical decomposition of the total scope of work to be carried out by the project team to accomplish the project objectives and create the required deliverables
  Contains every single thing that anyone on the project team will do
  Derived from
    Project scope statement
    Requirements documentation
    Organizational process assets
    Enterprise environmental factors

## Slide 16: Create Work Breakdown Structure (WBS)
Breaking down the work
Hierarchical and incremental
2 approaches
  Product based
  Activity based
Not much between the two approaches in practice since nearly all activities will generate a product and all products will be the result of some activity(ies).
Create Work Breakdown Structure (WBS)

## Slide 17: Create Work Breakdown Structure (WBS)
Product breakdown structure diagram
Holiday Cottages UK E-booking system
2. Network control centre
3. E-booking software
4. IT infrastructure products
5. Acceptance test products
2.1 Room
2.2 Staff
3.1 Business process models
3.2 Interface design
3.3 Application software
3.4 Usability products
4.1 New infrastructure plan
4.2 New servers
5.1 Acceptance test cases
5.2 Acceptance test results
3.2.1Style guide
3.2.2 Site map
3.2.3 Wireframe models
3.4.1 Usability test plans
3.4.2 Usability test results
Based on Bob Hughes, Project Management for IT related Projects, Figure 2.1, page 35
1. Project management plan
Every work package has a unique number, which identifies each work package and its category
The work package is the lowest level on a WBS.
Create Work Breakdown Structure (WBS)

## Slide 18: Create Work Breakdown Structure (WBS)
Activity breakdown structure diagram
Holiday Cottages UK E-booking system
2. System design
3. System implementation
4. Infrastructure
5. Product testing
3.1 Create web site front-end
3.2 Create web site back-end
3.3 Create test plans
3.4. Create user documentation
4.1 Acquire and refurbish server room
4.2 Purchase and install network and server hardware
5.1 Develop functional, acceptance and user test cases
5.2 Perform functional, acceptance and user testing
3.2.1
Database implementation
3.2.2 Create admin software
3.4.1 Write database administrator software guide
3.4.2 Write content management guide
Based on a diagram presented in “Head First PMP – A brain friendly guide”, Jennifer Greene and Andrew Stellman
1. Project management
Create Work Breakdown Structure (WBS)

## Slide 19: Create Work Breakdown Structure (WBS)
Note
  The WBS helps the project team see the magnitude of the work that needs to be done
  It helps catch packages that might not be so easily found in a document
  It does not establish the order that the team will perform each work package
Create Work Breakdown Structure (WBS)

## Slide 20: Create Work Breakdown Structure (WBS)
Decomposition
  Creating the WBS involves starting with major deliverables and coming up with work packages that will create them. This process is called decomposition.
  Decomposition involves:
    Start with a major deliverable
    Break down into progressively smaller pieces. It is important to organize this based on how you/your team/your organization works.
    When to stop?
      Each work package has to be compact enough to make it easy to organize (e.g. schedule, allocate resources, estimate cost)
    At the end of decomposition you end up with a collection of work packages that add up to the major deliverable
Create Work Breakdown Structure (WBS)

## Slide 21: Decomposition example
Organize wedding reception
Food
Wedding breakfast
Evening buffet
Decor
Table centrepieces
Table place settings
Flowers
Lighting
Entertainment
Music
Song list
Band
DJ
Band

## Slide 22: Create Work Breakdown Structure (WBS)
A description of each work package is held in the WBS dictionary
A work package description might look something like this:
Work package ID - 7.3 Work package name – TEST SOFTWARE
Statement of work
Verify that the new software has implemented all its requirements.
Each requirement will be tested by a team of quality engineers.
Quality requirements
The software must meet requirements defined by quality standards document QAStandards108a.
Required resources and cost estimate
Test planning – 1 QA lead and 2 QA analysts (£11,000)
Functional testing – 2 leads, 3 analysts, 7 testers (£38, 000)
Beta testing – 2 leads, 1 analyst (£5,000)
These are just some of the items of information that might be held for each work package
Create Work Breakdown Structure (WBS)

## Slide 23: Create Work Breakdown Structure (WBS)
Project Scope Baseline
  When project starts, and then progresses, it is important to be able to compare how the project is doing against what was planned
  The project scope baseline is what progress is compared against
  It consists of
    Project scope statement
    WBS
    WBS dictionary
  Changes can be made to the baseline, but only through project approved change management processes
Create Work Breakdown Structure (WBS)

## Slide 24: Control Scope
It is almost impossible to predict every piece of work that will need doing as part of a project
At some point, change needs to happen
The control scope process ensures that you make only those changes that you need to make, and that all stakeholders are clear on what the consequences will be
Helps avoid scope creep

## Slide 25: Control Scope
Baseline defines what the project team is supposed to do
Any change to the project means the baseline has to change
Process
  A problem is identified, change is needed
  Formal (documented) change request
  Change approved
  Variance analysis (how big is this change?)
  Re-plan the work
  Create a new baseline
  Change complete
Control Scope

## Slide 26: Validate Scope
Project is finished (maybe)
Did the team deliver the right product?
Validate cope process involves all project stakeholders gathering to make sure that all the work really has been done
Inputs to the process include Requirements documentation, Traceability matrix, Deliverables and Project Management plan
If the team did the work right, the stakeholders formally accept (i.e. in writing) the deliverables – the product is now ready to GO!
If the stakeholders don’t think that all work was done, then changes will have to be made.
Validate Scope

## Slide 27: Acknowledgement
Lecture material based on ideas presented in
  “Project Management for IT-Related Projects” , Bob Hughes (editor), 2012, BCS, ISBN 978-1-78017-118-0
  “Head First PMP – A brain friendly guide”, Jennifer Greene and Andrew Stellman, 2013, O’Reilly, ISBN 978-1-449-36491-5

## Slide 28: What next?
Time management