## Slide 1: Project Management & Research Methodology (IS4S706)
Resource Management

## Slide 2: This video
Resource management
Resource and the project schedule
  Crashing the critical path
  Resource clashes

## Slide 3: What is resource management?
The processes used to identify, acquire and manage the resources needed for the successful completion of a project.
PMBOK’s 6 processes
  Plan resource management
  Estimate activity resources
  Acquire resources
  Develop team
  Manage team
  Control resources

## Slide 4: Plan resource management
First step of resource management.
Involves deciding what tools and techniques that will be used in the subsequent steps.
Usually only performed once, at the start of a project.

## Slide 5: Estimate activity resources
Identifies what resources are required by the project.
Carried out at the project activity level
  People, skills, qualifications, certification
  Hardware, software
  Facilities – that is, each project activity is scrutinized
Identifies type, quantity and characteristics of resources
Relies on
  Activity list
  Activity attributes
  Resource costs
Generally done at start and also reviewed

## Slide 6: Acquire resources
Obtaining the people, equipment, software and other resources need to deliver the project.
Can be bureaucratic and time consuming – so should take place as early as possible in the project cycle
Guides the selection of resources and assigns them to their respective activities.
Uses project schedule

## Slide 7: Develop team
People are main resource on many IT projects.
Often part of the team.
Project team needs to be motivated and on-side.
Teamwork is a crucial factor for project success.
Improving knowledge and skills
Increase trust and agreement
Dynamic, cohesive and collaborative team culture
Empowering the team

## Slide 8: Manage team
Project team key resource.
Monitoring and tracking team members
Identify issues and address problems.
Influences team behaviour
Manages conflict and resolves issues
Responsibility of the Project Manager
  strong leadership
  emotional intelligence.

## Slide 9: Control resources
Ensures that resources that are assigned and allocated as planned.
Monitoring and controlling planned usage against actual usage and taking corrective actions when required to keep the project on track.
Ensures that correct resources are available to correct tasks at the correct times
Should be performed continuously in all project phases

## Slide 10: Resource and the project schedule
Crashing the critical path
Resource clashes

## Slide 11: Meeting the deadline
Why project deadlines might be tight
  Delay in one or more tasks
  Unrealistic task durations in project plan
    Estimates were wrong
    Wanted to win a contract
  Commercial pressure

## Slide 12: How to meet a deadline?
Crash the critical path
  A schedule compression technique
  How does it work?
    Identify critical activities that can be completed sooner by adding extra resource
    Assign extra resources (usually people)
      Overtime
      Contractors
Bear in mind that crashing the critical path can result in a new critical path

## Slide 13: Crashing the critical path by allocating more resources
A (10)
D (10)
B (10)
E (15)
C (20)
F (5)
Critical path A, B, C, F
Project duration = 45 days
A (10)
D (10)
B (10)
E (15)
C (16)
F (5)
Add resources to activity C.
It’s duration is now 16 a reduction of 4.
Critical path is still A, B, C, F
Project duration = 41 days.
Project finishes 4 days earlier than original plan.

## Slide 14: Crashing the critical path by continuing to allocate more resources
A (10)
D (10)
B (10)
E (15)
C (16)
F (5)
Critical path A, B, C, F
Project duration = 41 days
A (10)
D (10)
B (10)
E (15)
C (5)
F (5)
Add resources to activity C.
It’s duration is now 5, a reduction of 11.
Critical path A, D, E, F
Project duration = 40 days.
Project finishes 1 day earlier than previous plan.

## Slide 15: Split activities into sub-activities to collapse the critical path
Write
Software
(10)
Write user
Documentation
(10)
20 days
Write
Data Entry
Software
(5)
Write
Report
Software
(5)
Write
Data Entry
Documentation
(5)
Write
Report
Documentation
(5)
15 days

## Slide 16: Other ways to meet the deadline
Phase 1
Phase 2
Phase 3
Live use of parts of the system
Trim the scope (strongly deadline-driven projects)
  Can the customer do without the bells and whistles?
  Time-box the project (time is fixed, scope varies)
Phase the implementation
  the customer might be happy to take only part of the system by the “deadline” while you work on the rest for later implementation

## Slide 17: Resource allocation
So far we have assumed that the project has sufficient resources available to carry out tasks according to the schedule
In practice, the availability of suitable resources needs to be considered. These resources include
  Labour
  Tools & equipment
  Material & supplies
In IT projects, the main concern is usually with labour (i.e. people)
If certain resources are limited, then some activities might have to be delayed
Resource allocation attempts to allocate available resources in such a way as to limit impact on the project plan

## Slide 18: Resource types
On this module, resource type is a reference to a skill or
  For example
    Activity: Write C++ software component
    Resource type: Programmer
  For example
    Activity: Recruit staff
    Resource type: HR manager

## Slide 19: Activity network
In the activity network below, 3 resource types have been identified – System designer, Programmer and Tester.
The resource types have been allocated to activities
System designer
System designer
System designer
Programmer
Programmer
Programmer
Tester

## Slide 20: Resource by day table
Records the numbers of each resource type needed on each dayy

## Slide 21: Resource histograms

## Slide 22: Resource clashes
In some cases we may find that the project plan needs more resource of a particular type than are available
  This results in a resource clash

## Slide 23: Example
3 system designers needed on day 1.
1 system designer needed on day 2.
What if only 2 system designers available?

## Slide 24: Resolving a resource clash
Possible options to resolve clash
  Smooth: Use the float of an activity to delay its start until the required resource becomes available
  Level: Delay the start of activity even though float is used up. This will delay completion of project, but might be preferred to extra cost of increasing resources
  Buy in additional resources (staff) to cover the deficiency. This will probably increase project cost

## Slide 25: Example
3 system designers needed on day 1.
1 system designer needed on day 2.
What if only 2 system designers available?

## Slide 26: Smoothing solution
Activity 3 has float>0 so pushed back by a day
Activity 4 also forced back, but it too has float>0
Resource clash resolved – we now only need a maximum of 2 system designers on any given day
Project remains on schedule
Notice the System designers histogram is “smoother”

## Slide 27: Levelling solution

## Slide 28: Add resource solution
Contractor £££££

## Slide 29: Example
Programmer
Programmer
Programmer
Programmer
What if only 2 programmers available to the project?
Programmer
Programmer

## Slide 30: Smoothing solution – delay activity 2

## Slide 31: Review
 Screen
We have looked at several techniques for time planning
  Meeting tight deadlines
    crashing the critical path
    trimming the scope
    phasing implementation
  Resource smoothing and levelling
    remember, real projects have many tasks, some of which may require resource rescheduling due to smoothing and levelling

## Slide 32: What next…
Cost planning
Cost management
Coursework…..