## Slide 1: Project Management & Research Methodology (IS4S706)
Estimating

## Slide 2: Estimating
What do we need to estimate?
  Time
  Cost
  Resources
If you want to delve deeper
  http://courses.cs.washington.edu/courses/cse403/07sp/assignments/estimationbasics.pdf

## Slide 3: Estimating Resources
Identifies what resources are required by the project.
Carried out at the project activity level
  People, skills, qualifications, certification
  Hardware, software
  Facilities – that is, each project activity is scrutinized
Identifies type, quantity and characteristics of resources
Relies on
  Activity list
  Activity attributes
  Resource costs
Generally done at start and also reviewed
Coordinated with other processes
e.g. Activity: Develop web site GUI
  Web developer (10 days)
  Adobe Dreamweaver
  Apple iMac

## Slide 4: Estimate Costs
How much will the project cost?
Inputs include
  Project activity list (e.g. WBS + activity descriptions)
  Project schedule (activity duration and resource requirements)
  Organizational factors
How much will each project activity costs?
  Apply appropriate technique

## Slide 5: Cost Estimating Tools and Techniques
Quotes (preferred suppliers?, consider options)
Organizational procedures / rates
How long will it take? (cost = daily rate x number of days)
  Analogous
  Parametric
  Expert judgement
  Three-point
    optimistic, most-likely, pessimistic
Vendor bid analysis
Reserve analysis
Project management software

## Slide 6: Estimating cost outputs
For each project activity
  Cost estimate
  Basis of estimate
Activity: Develop GUI
Web developer
Dreamweaver license
iMac
10 days
£7,560.00

## Slide 7: Estimating time
Allocating an estimated duration to the activities of a project
  Allows us to calculate overall duration of the project
  Allows us to identify when (and for how long) we need to call upon the services of individuals to carry out particular tasks
    a major contributor to the cost of IT projects

## Slide 8: When are estimates carried out?
At the start
Throughout the project
  Activities change
  As the project proceeds, accuracy and detail will be improved

## Slide 9: Under estimating
If time, cost and resources are under estimated a project can fail
  Delayed beyond its agreed completion date
  Exceeds budget
  Quality of deliverable suffers

## Slide 10: Over estimating
If time, cost and resources are over estimated
  A bid to carry out work for external customer might be rejected due an excessively high estimate
    Failure due to estimated cost not being competitive
  Generous estimate may lead to lower productivity
    Parkinson’s Law (‘work expands to fill time available’)
  Excess time, resource and money could have been used more productively elsewhere

## Slide 11: Estimating is not easy
Estimation required at the start of a project
  That’s the time at which we have the most uncertainty
The cone of uncertainty (Barry Boehm, Software Engineering Economics, Prentice Hall, 1981)
  Uncertainty greatest at the start
  Variance of 4x to 0.25x in range
  For example, a project estimated to last 1 year could actually take as long as 4 years or as short as 3 months
  As the project proceeds accuracy and detail will be improved

## Slide 12: Travelling home example
It usually takes me an hour to get home by car
My quickest time to date is 45 minutes
My slowest time to date is over 5 hours
My estimate at the start of the journey will usually be wrong
An estimate 5 miles from home will usually be very accurate

## Slide 13: Implications
Make sure estimates are as accurate as they possibly can be when putting project plan together
However
  Revisit the project
  Contingency

## Slide 14: Estimating methods
Expert judgement
Analogy
Parametric approaches
Scrum techniques
3-Point
  How many sweets
  in the jar?

## Slide 15: Expert judgement
Ask somebody who is familiar with the tasks to be carried out, somebody who is an expert
Advantages
  Involves the people with the best experience of similar work in the past
Problems
  What if the task is “new”, so no prior experience
  Experts can be prone to human error – e.g. they may underestimate in case a larger figure suggests they are less capable
  It can be difficult for project planner to evaluate the quality of somebody else’s estimate

## Slide 16: How long will it take 1 person to eat all the sweets? Expert.
Physiologist: In my expert opinion, an average person could eat 1 cola cube every 2 minutes.
Shopkeeper: I sell sweets for a living. In my expert opinion, there are 200 sweets in the jar.
Time = 200 x 2 minutes = 400 minutes

## Slide 17: Estimating by analogy
What if no experts available?
An alternative approach is the analogy (or comparative) approach
Analogy approach involves
  Identify key characteristics of new project
  Search for previous project with similar characteristics (if no past project exists that matches new, it might be necessary to select parts of old projects that match parts of new)
  Use actual effort recorded for previous project as basis for estimating new one
  Identify key differences between the old and new project
  Adjust the base estimate to take account of these differences

## Slide 18: How long will it take 1 person to eat all the sweets? Analogy.
Jars of sweets have been eaten before !
Similar sized jar, different sweets – 4 people at all the sweets in 20 minutes.
Similar sweets, different sized jar – 1 person ate the lot in 130 minutes !
Time = 300 minutes

## Slide 19: Parametric approaches
Project data used as input a formula or computer program that subsequently produces an estimate.
Make use of a model derived using data from previous project
Uses a statistical relationship between the historical data and other variables
Estimation is based on the value of certain parameters or variables
  Size drivers

## Slide 20: Function point analysis
Function point analysis Mk II
  A measure of the functional size of a software application
  Count the inputs, outputs and data entities accessed
  Adjust the function points for technical complexity
    Weight the counts to take account of relative difficulty of implementing (e.g. output tends to be easier than input, since input requires error checking)
    In Mark II method, weightings are
        inputs 0.58
        outputs 0.26
        entities accessed 1.66

## Slide 21: Function point example
In a proposed E-Booking system there is a transaction that records the final payment made by a customer for a booking for which they have already paid a deposit
  There are 2 inputs for the payment
    Booking number
    Amount paid
  There are 3 possible outputs
    Payment reference number
    Customer name
    Error message
  There are 2 data entities
    Customer table
    Booking table

## Slide 22
  The function point count (FPC) for this transaction is
    (2 x 0.58) + (3 x 0.26) + (2 x 1.66) = 5.26
  What does 5.26 mean in this context?
    For a single transaction, not very useful
    But, if all the FPCs for the proposed system are added, it gives a useful measure of the size of a project
    Looking back at previous projects, we can work out how many function points are implemented per day on average (e.g. it may turn out to be 40)
    When new project is analysed, then it is possible to estimate number of days to complete
      (FPC total)/average FP per day
      So, a project with 2400 function points would take approx. 2400/40 = 60 days

## Slide 23: How long will it take 1 person to eat all the sweets? Parametric.
Jars of sweets have been eaten before !
Number of sweets = Volume of Jar
Volume of 1 sweet
Consumption rate = 1 sweet every 1.5 minutes
Time = 60 x 60 x 140 x 1.5 mins = 437 mins
12 x 12 x 12
14mm
60mm
60mm
12mm
12mm
12mm

## Slide 24: Estimating in Scrum
Scrum doesn't impose the use of estimation techniques.
Important to
  Estimate how much work can be done in a Sprint
  Update estimate during Sprint
Relative Story Point Estimation
  Numeric Sizing (1, 2, 3, 5…., 10)
  T-shirt sizes (XS, S, M, L, XL XXL, XXXL)
  Fibonacci Sequence (1, 2, 3, 5, 8, 13, 21 etc)
Estimating
  Planning poker
  https://www.youtube.com/watch?v=_jYiuYtrpp8
XS
S
M
L
XL
XXL
XXXL

## Slide 25: How long will it take 1 person to eat all the sweets? Poker.
Time = 377 min
Estimator 1
Estimator 2
Estimator 3
Estimator 4
Estimator 5
377
377
233
610
144
377
377
233
377
233
377
377
377
377
377
Round1
Round2
Round3

## Slide 26: Three-point estimates
Three estimates
  Most likely
  Optimistic
  Pessimistic
Use the average
Triangular
  Estimate =
O = 5, ML = 10, P = 22
  Estimate = = 12.33
    Optimistic + Most Likely + Pessimistic
3
    5 + 10 + 22
3

## Slide 27: PERT (Program Evaluation and Review Technique)
PERT / Beta distribution
Optimistic and Pessimistic less likely than Most likely
Estimate =
O = 5, ML = 10, P = 22
  Estimate = = 11.7
    Optimistic + (4 x Most Likely) + Pessimistic
6
    5 + (4 x 10) + 22
6
*

## Slide 28: How long will it take 1 person to eat all the sweets? 3-Point.
Best case:
Person is really, really hungry.
Time = 200 minutes
Worst case:
Person has just eaten a large Sunday dinner.
Time = 600 minutes
Expected case:
Time = 310 minutes.
Time = 200 + 4x310 + 600 = 340 minutes
6

## Slide 29: Reserve Analysis
So far, we have assumed things will go according to plan
  Activities starting and finishing when they are supposed to, and taking no longer than the estimated time
However
  Things can go wrong
  Estimates are only estimates
Prudent project manager will allow some additional margin, or contingency

## Slide 30: Allocating contingency to tasks
Traditional approaches insist that, in order to meet a promised deadline:
  every task must start and finish exactly on published dates
  therefore every task must have contingency (or safety)

## Slide 31: How much safety?
Again, this will have to be estimated
Will be governed to some extent by how much risk you are willing to take
% of Expected
Westheimer's Rule
  “... multiply that figure by two and change the unit of measure to the next higher unit. So, in this way, you allocate two days to a one hour task.”
Use PERT*
  Standard Deviation = (Pessimistic - Optimistic)/6
  Add SD as safety to Expected for 68% confidence
  Add SDx2 as safety to Expected for 95% confidence
  Add SDx3 as safety for to Expected 99% confidence

## Slide 32: A problem with adding contingency to tasks
Parkinson’s law
  work expands to fill the time available to it
Student’s syndrome
So
  In order to meet the project deadline we force team members to meet each task deadline
  Therefore each task probably needs a safety margin
  Consequently team members don’t start on time and don’t focus on the task
  Consequently when things go wrong, some tasks finish late, despite the safety margin
Some tasks finish late, none finish early, meaning the project over-runs

## Slide 33: Critical Chain with Buffer Management (CCBM)
Removes the “safety” from individual tasks
Safety summed and buffer placed the end of the critical path

## Slide 34: CCBM with PERT*
Activity duration SD (Sigma) = (P – 0) / 6
Activity Variance (Var) = (Activity Sigma)2
Project Var = Sum of all Activity Var
Project Sigma = (Project Var) ½
No project buffer, project duration = 130.5 (50% confidence)
Project buffer = Project Sigma = 8.74 (68% confidence)
Project buffer = 2 x Project Sigma = 17.5 (95% confidence)
Project buffer = 3 x Project Sigma = 26.2 (99% confidence)
Assumes some activities will finish earlier than Expected

## Slide 35: Closing remarks
Estimating is important
  Time, cost, risk…..
Estimating can be difficult
Variety of methods exists
  Pick most appropriate
  Use more than 1 method
  Seek out a range of opinions
Estimates will always include error
  Keep a close eye on the schedule
  Contingency
  Re-visit estimates as project progresses

## Slide 36: Next topic
Risk management
Thanks for listening

## Slide 37: Stinger…
Normally, the class tries these techniques out on a real jar of sweets.
More often than not, the winner is…..
  The Wisdom of Crowds - Wikipedia