## Slide 1: Project Management & Research Methodology (IS4S706)
Risk Management

## Slide 2: Outline
What is risk?
Risk management
  Identifying risk
  Assessing the risk
    Quantitative approaches
    Qualitative approaches
  Taking action
  Monitoring and control

## Slide 3: What is risk?
PRINCE2 definition
  “The chance of exposure to the adverse consequences of future events”
  Chance
    It’s something that might happen
  Adverse consequences
    e.g. reduction in value of project, failure of project (higher development costs, delayed completion, reduced scope, reduced performance), less competitive system, failure to meet appropriate capability
  Future events
    It hasn’t yet happened – still time to make plans

## Slide 4: Risk management
A continuous process, throughout the life of a project
Involves
  Identify issues (root causes)
  Identifying risk
  Assessing risk
  Make plans to deal with risk
  Monitor and control risk
  Initiate actions when required

## Slide 5: Identifying Risk – How?
Detect every possible risk
Information gathering
  Brainstorming
  Interviews
  Root cause identification
  Documentation reviews
  Assumption analysis
  Checklist analysis

## Slide 6: Identifying Risk – Where?
Where to look?
  Resources
  The Critical Path
  Assumptions
  Estimates
  Outside the project
  Generic risks

## Slide 7: Generic risks
Barry Boehm’s “Top ten software project risks”
  Personnel shortfalls
  Unrealistic schedules and budgets
  Developing the wrong functions and properties
  Gold-plating
  Continuous stream of requirements changes
  Shortfalls in externally furnished components
  Shortfalls in externally performed tasks
  Real-time performance shortfalls
  Straining computer science capabilities
Not all generic risks will be relevant

## Slide 8: Property development example
Bobby is about to hand in his notice at work in order to embark on a career in property development. He is planning on buying his first property. He has enough money saved for the deposit, the building work, and, at most, 9-months of mortgage repayments. There is quite a lot of development work needed, but he has friends in the building trade who have promised to help at reasonable rates. In any case, he thinks he’ll be able to undertake lots of the work himself – after all, how hard can it be!?. The property to be purchased is currently a single dwelling 3-storey house. Bobby is hoping to get planning permission to convert to 3 one-bedroom flats. The plan is to get to the flats ready for rent within 6-months (i.e. next May). The market for one-bedroom flat rental is buoyant at the moment – lot of young professionals live and work in the area - so he is anticipating making a large profit.

## Slide 9: Property development – generic risks
Interest rates sometimes go up
Property market fluctuates
Builders let you down
Gold-plating (do you really need the expensive kitchen?)
Cost estimates are nearly always an underestimate
DIY usually takes longer than you expected
Poor weather
Project bottlenecks (plasterer can’t start until the electrician has finishes)
Planning permission delayed or rejected

## Slide 10: Drone Survey Project- risks
Risk
1. Interest rates can go up, mortgage repayments can increase
2. Builder friends are not available
3. Planning permission is turned down
4. Bobby can’t do the work – its not as straightforward as he thought
5. Work takes longer than 6-months – its winter after all
6. Bobby gets ill
7. Slump in the market for 1-bedroom flats so cannot sell (or not as much profit, maybe even a loss)
8. Expected work costs more than planned (unexpected costs)
9. Extra work increases costs(Gold Plating)

## Slide 11: Assessing the risk
It might not be possible to take action for all possible risks identified
Therefore need to prioritise
But first, we need to evaluate the risk
Risk evaluation based on
  The probability that an event that leads to harm will occur
    e.g. 10% chance, very likely, not much chance
  The adverse impact the event will have, should it occur
    e.g. an extra 10 days on the project, 25% increase in project costs, scope of project will have to change
  Probability and Impact combine to give Risk Exposure

## Slide 12: Measuring Risk Exposure
2 general approaches
  Quantitative
    Probability value (e.g. 0.4)
    Monetary value (e.g. £50,000)
  Qualitative
    Qualitative descriptions (e.g. “Very low”, “Medium”

## Slide 13: Measuring risk exposure
Quantitative
  Probability and impact can be multiplied to create a risk exposure
    risk exposure = impact x probability
  Example
    if there is a 0.1 probability of hardware component failing and the impact of such a failure is £25,000 then
      risk exposure = £25,000 x 0.1 = £2,500

## Slide 14: Measuring risk exposure
Quantitative ordered list
Risk id | Description | Probability | Impact £ | Exposure £
3 | Planning permission is turned down | 0.4 | 20000 | 8000
5 | Work takes longer than 6-months | 0.8 | 8000 | 6400
4 | Bobby can’t do the work | 0.2 | 12000 | 6000
1 | Interest rates can go up | 0.7 | 5000 | 3500
8 | Expected work costs more than planned | 0.3 | 9000 | 2700
6 | Bobby gets ill | 0.4 | 4000 | 1600
7 | Slump in market, cannot sell | 0.1 | 11000 | 1100
2 | Builder friends are not available | 0.1 | 10000 | 1000
9 | Extra work increases costs(Gold Plating) | 0.1 | 1000 | 100

## Slide 15: Measuring risk exposure
Qualitative
  Agreed terms: High, Significant, Medium, Low
  Discuss (team, experts, stakeholders)
Risk id | Description | Probability | Impact
1 | Interest rates can go up | High | Significant
2 | Builder friends are not available | Low | High
3 | Planning permission is turned down | High | High
4 | Bobby can’t do the work | Low | High
5 | Work takes longer than 6-months | Medium | High
6 | Bobby gets ill | Medium | Medium
7 | Slump in market, cannot sell | Low | High
8 | Expected work costs more than planned | Significant | Medium
9 | Extra work increases costs(Gold Plating) | Low | Low

## Slide 16: Measuring risk exposure
2, 4, 7 | 5 |  | 3
 |  |  | 1
 | 6 | 8 | 
9 |  |  | 
Low
Medium
Significant
High
Medium
Low
Significant
High
Impact
Probability
Legend | 
Priority level 1 | 
Priority level 2 | 
Priority level 3 | 
Priority level 4 | 
Tolerance Line
Qualitative ordered list Probability Impact Grid

## Slide 17: Taking action
Project uncertainty due to identified risks can be reduced by taking mitigating action
  Accept the risk
  Prevent the risk
  Reduce the risk
  Transfer the risk
  Contingency
A mitigating action will mean revisiting and updating
  the project plan
  the development costs
  the functional scope

## Slide 18: Taking action
Accept the risk
  Take no action (other than monitor)
  Reasons
    Risk exposure is low
      Risk probability is low
      Impact is acceptable
    No other appropriate action available
    Cost of action outweighs the impact cost

## Slide 19: Taking action
Prevent the risk
  Also known as risk avoidance
  How?
    Change the activity from which the risk originates
    For example
      Activity: Develop a particular software component using C++.
      Risk: Project team has very limited experience with C++ and so quality of the work is likely to be compromised.
      Risk prevention: The project team has plenty of C# development experience. It is therefore decided to develop this particular software component using C# - there is no obvious reason for this switch to compromise the project.

## Slide 20: Taking action
Reduce the risk
  Reduce the probability of the risk occurring
  and/or
  Reduce the impact of the risk
  For example
    Activity: Data collection (drone survey)
    Risk: Drone can only be flown in good weather. Poor weather will result in data collection being delayed.
    Risk reduction: Schedule data collection for no earlier than May and no later than September.

## Slide 21: Taking action
Transfer the risk
  Shift the risk to another party
  For example
      Activity: Install new server and network hardware/software.
      Risk: This activity is on the critical path. The project team has some experience but have some concerns that work might take longer than planned.
      Risk transfer: Contract the work out to specialist company. As part of the contract, make sure that costs associated with over-runs are transferred to the specialist company.

## Slide 22: Taking action
Contingency
  Take no action before the risk occurs
  However,
    Plan an action to be taken once the risk occurs (or when the probability of risk occurring becomes high)
    For example
      Activity: Database implementation.
      Risk: Only 1 database specialist on the project team. Team members sometimes get ill. Completion of work will be delayed if the database specialist becomes unavailable.
      Contingency: Identify staff in other teams who could cover the role in the event of the database specialist becoming ill. Creating the conditions in which the contingency action can take place will need to be managed.

## Slide 23: Taking Action – is it worth it?
Taking action comes at a "cost"
  Financial cost
  Scope change
  Schedule change
Do the benefits gained by the action outweight its associated cost.
Quantitative
  Risk reduction leverage
    RRL = (REbefore – REafter)/cost
  If RRL is greater than 1.0, it means the reduction action is probably worth taking

## Slide 24: Risk reduction leverage
Example:
  Risk: Drone gets irreparably damaged during survey
    Impact = £5000
    Probability = 0.1
    Exposure (before) = £5000 x 0.1 = £500
  Action: Insure drone at a cost of £250
    Impact = £200 (excess)
    Probability = 0.1
    Exposure (after) = £200 x 0.1 = £20
  RRL = (REbefore – REafter)/cost = (500 – 20)/250 = 1.92

## Slide 25: Project go-ahead?
Do not give go-ahead if there are any activities above a project specific tolerance line
Action must be taken to ensure a new position in the grid that is below the tolerance line

## Slide 26: Monitoring and control
Risk management continues throughout the life of the project
  New risks may be identified
  Secondary risks arising from actions to reduce initial risk
Monitoring risk should be part of the project control cycle
  Regular reviews
  Reviews after significant events
Documentation
  Risk register
  Risk record

## Slide 27: Monitoring and control
Risk register
Number | Description | Owner | Probability | Impact | Action | Status | Last updated
1 | Slow response times due to lack of expertise in temporal database design | D. Evans | Low | High | Get expert opinion on database and query design | On-going | 3/9/2015
2 | Updated spatial data not available in time for system deployment | R. Smith | High | Medium | Make sure that earlier version of data is available | Done | 5/8/2015
3 | Implementation delay due to non-availability of specialist staff | R. Smith | Medium | Medium | Employ short-term contract staff on attractive terms to cover | Contingency – contractors’ details are in place | 5/8/2015
: | : | : | : | : | : | : | :
: | : | : | : | : | : | : | :

## Slide 28: Monitoring and control
Risk record
From Hughes (2012)

## Slide 29: Summary
Most (if not all) projects will carry risk
Structured risk management will help reduce the impact of these risks
Managing risk is a continuous process
It involves
  Identifying risks
  Establishing
    Probability
    Exposure
    Priority
  Determine and plan remedial actions
  Monitoring

## Slide 30: What to do next?
Risk management tutorial
Coursework !!!
Next topic….
  Quality Management
  Thanks for listening

## Slide 31: Acknowledgement
Lecture material based on ideas presented in
  “Project Management for IT-Related Projects” , Bob Hughes (editor), 2012, BCS, ISBN 978-1-78017-118-0
  “Head First PMP – A brain friendly guide”, Jennifer Greene and Andrew Stellman, 2013, O’Reilly, ISBN 978-1-449-36491-5